## Risk Register_Week4
Risk Register
AI-Assisted Triage Decision-Support Tool ¦ Mercer General Hospital ¦ Zhanna McDonald ¦ Week 4
Likelihood / Impact; H = High M=Medium L=Low ¦ Categories: AI-Technical, Operational, Ethical, Equity ¦ Every mitigation answers: who, when and what happens if it fails
# | Risk Name | Category | Likelihood | Impact | Mitigation | Signal of Success
R1 | Poor Model Performance at Hospital Sites | AI Technical | H | H | The machine learning (ML) Engineer tests the model before it is used at a hospital. If the model's accuracy for identifying ESI Level 1 & 2 patients drop more than 3%, the supervisor reviews the results. The model is paused until it is approved. | Accuracy for ESI Level 1 & 2 patients stays within 3% during quarterly reviews.
R2 | Use of Information Unavailable at Triage | AI Technical | M | H | The ML engineer checks that the model only uses information available during triage. The supervisor approves the checklist before training begins. If there are any information that should not be included is found, the model is retrained. | The completed checklist is approved before training and no data leakage is identified.
R3 | Alert Fatigue from False Alarms | Operational | M | H | The ML engineer sets a minimum accuracy level of ≥60% before the tool is deployed. The Project Manager reviews how often clinicians responds to each alert every week. If staff begin ignoring alerts, the alert setting is adjusted. | Clinicians respond to at least 70-80% of alerts each week during the 12-week pilot.
R4 | Workflow Abandonment During Night Shift Understaffing | Operational | H | M | In consultation with Sister Patrice Alleyne (Director of Nursing), the ML tool only uses information nurses already collect during triage. The project managers observe its use during two night shifts each week. If the nursing staff uses the tool less often, then the workflow is reviewed and improved | The tool is used in at least 80% of triage assessments across all shifts and nurses report that no extra work has been added.
R5 | Overreliance on AI Recommendations | Ethical | M | H | The tool displays descriptive risk flags, for example "High risk indicators detected: elevated heart rate, Sp02 is 87%, arrived by ambulance". It does not recommend the ESI level or replace clinical judgement. Before implementation, nurses completed a simulation training and must demonstrate that they can recognise incorrect alerts. If they do not pass the training, they must complete it again before using the tool. | At least 80% of nurses pass the simulation and monthly chart reviews show that nurses continue to use their own clinical judgement.
R6 | Patient Consent Gap Due to Lack of AI Disclosure | Ethical | L | H | The Project Manager prepares a verbal disclosure script and a written version for the patient information board. The Director of Nursing and a Patient Representative review and approve the disclosure before the model is implemented. All triage nurses will also receive training before deployment. | The verbal and written disclosure scripts are approved before implementation. All triage staff complete training and spot check during the first two weeks confirms that disclosure is provided in at least 90% of observation encounters.
R7 | Language and Literacy Barriers to Understanding AI Alerts | Equity | M | M | The IT Team and the Project Manager prepare, English, Creole and Spanish translations for all patients facing disclosure materials and flag labels. Having one creole and Spanish speaking clinician at Mercer General Hospital to review the translations before the model is implemented. The approved versions are stored in the project repository before it is deployed. | Translation approval is documented before the model is deployed. Disclosure materials are available in English, Creole and Spanish at the triage desk on the first day of implementation.
R8 | Underrepresentation of Elderly Patients with Atypical Symptoms | Equity | M | H | The ML engineer reviews the model's performance across different age groups. If the model performs worse for patients aged 65 years and above, nurses are prompt to rely on clinical judgement when assessing patients with atypical symptoms. | The model performs consistently across age groups or an approved clinical assessment is placed before implementation.
R9 | Reduced Model Accuracy During Sesonal Patient Surges | AI Technical | M | M | The ML engineer reviews the model's performance every month using recent patient data during seasonal surges. If the model's accuracy decreases by more than 3%, the supervisor reviews the results and the model is paused until it is recalibrated and approved. | Monthly performance reports show that model accuracy remains within 3% of baseline performances throughout the pilot period.
R10 | Unclear Responsibility for AI Errors | Ethical | M | H | The Project Manager appoints a Clinical Safety Manager before implementation. A written procedure explains who investigates AI-related incidents, how cases are reported within 48 hours and when the model must be paused. Staff review the procedure during pre-implementation training. | The Clinical Safety Manager is appointed before implementation. The incident review procedure is approved and a practice exercise is completed before the first patient is assessed using the model.
R11 | Incorrect Data Entered into the AI System | AI Technical | L | M | Triage nurses confirm key patient information before submitting it to the AI system. The IT Team implements automatic checks that flags unrealistic values such as extremely low oxygen saturation or blood pressure. If incorrect information is identified, it is corrected before the model generates an alert. | Weekly audits shows that incorrected patient information is identified and corrected before reachinf the AI system and no uncorrected data entry errors are found during the pilot.
How to read this register: Each row identifies a potential risk associated with the Ai-assisted triage tool and classifies it as AI Technical, Operational, Ethical or Equity. The Likelihood and impact columns rate each risk as High (H), Medium (M) or Low (L). The Mitigation column outlines the actions taken to reduce or manage the risk, while the Signal of Success column proivdes measureable evidence that the mitigation is effective and the risk remains under control.